## Dependence Calcs
cost | i | p
12 | 0 | 0
13 | 0 | 0
14 | 0 | 0
15 | 0 | 0.05
16 | 0.02 | 0.1
17 | 0.04 | 0.15
18 | 0.14 | 0.2
19 | 0.24 | 0.325
20 | 0.425 | 0.45
21 | 0.61 | 0.575
22 | 0.76 | 0.7
23 | 0.91 | 0.775
24 | 0.955 | 0.85
25 | 1 | 0.925
26 | 1 | 1
27 | 1 | 1
28 | 1 | 1

## Sensitivity Diagram
Probability | Base Plan Target | Mobilisation Delays | Unexpected Site Issues (Ecology, Archaeology, Contamination) | Unexploded Ordinance | Asbestos | Mechanical Failure of Rigs | Personnel availability for processing
0 | 58 | 47 | 47.5 | 48.5 | 49.5 | 50 | 50.3
0.05 | 58 | 48 | 48.5 | 49.5 | 50.5 | 51.5 | 52
0.1 | 58 | 49 | 49.5 | 50.5 | 51.5 | 53 | 54 | 2
0.15 | 58 | 49.5 | 50 | 51 | 52 | 54 | 55.5
0.2 | 58 | 49.5714 | 50.5714 | 51.5714 | 53.0714 | 55.5714 | 57.5714
0.25 | 58 | 49.6429 | 51.1429 | 52.1429 | 54.1429 | 57.1429 | 60.1429
0.3 | 58 | 49.7143 | 51.3143 | 52.3143 | 54.8143 | 57.8143 | 62.3143
0.35 | 58 | 49.7857 | 51.4857 | 52.4857 | 55.4857 | 58.4857 | 63.2857
0.4 | 58 | 49.8571 | 51.6571 | 52.6571 | 55.6571 | 58.6571 | 63.6571
0.45 | 58 | 49.9286 | 51.8286 | 52.8286 | 55.8286 | 58.8286 | 63.9286
0.5 | 58 | 50 | 52 | 53 | 56 | 59.5 | 64.5
0.55 | 58 | 50.25 | 52.35 | 53.35 | 56.35 | 60.35 | 65.35
0.6 | 58 | 50.5 | 52.8 | 53.8 | 56.8 | 60.8 | 65.8
0.65 | 58 | 50.75 | 53.05 | 54.55 | 57.55 | 61.55 | 66.55
0.7 | 58 | 51 | 53.5 | 55.5 | 58.5 | 62.5 | 67.5
0.75 | 58 | 51.5 | 54.2 | 57.2 | 59.7 | 63.7 | 68.7
0.8 | 58 | 52 | 54.8 | 58.8 | 60.8 | 64.8 | 69.9
0.85 | 58 | 52.5 | 55.5 | 60.5 | 62 | 66.5 | 71.7
0.9 | 58 | 53 | 57 | 62.5 | 63.5 | 68 | 73.3
0.95 | 58 | 55 | 59 | 65 | 66 | 70.5 | 75.9
1 | 58 | 57 | 62 | 69 | 70 | 74.5 | 80
Wk 58 = Base plan target

## Schedule Sensitivity
Time scale:
Wk0 – Contractor Appointed & Engineer Representative Appointed
Wk 4 – Start of site works
Wk 17 – High priority site works complete
Wk 26 – Factual report on high priority works
Wk 38 – Interim Interpretative report on high priority works
Wk 42 – Low Priority Site works complete
Wk 55 – Completion of factual report for all works
Wk 68 – Completion of Final Interpretative Report
probability | M1 Site Mobilisation | M1 Uncerainty | M2 High Priority (HP) Works Complete | M2 Uncertainty | M3 HP Factual Report | M3 Uncertainty | M4 Low Priority (LP) Works Complete | M4 Uncertainty | M5 Factual Report Full | M5 Uncertainty | M6 Interpretative Report Published | M6 Uncertainty
0 | 4 | 2 | 17 | 14 | 26 | 20 | 42 | 30 | 55 | 50 | 68 | 50
0.05 | 4 | 2.3 | 17 | 15 | 26 | 22 | 42 | 32 | 55 | 52 | 68 | 55
0.1 | 4 | 2.5 | 17 | 16 | 26 | 23 | 42 | 34 | 55 | 53 | 68 | 58
0.15 | 4 | 2.7 | 17 | 17 | 26 | 24 | 42 | 35 | 55 | 53 | 68 | 60
0.2 | 4 | 3 | 17 | 18 | 26 | 25 | 42 | 36 | 55 | 53.3 | 68 | 62
0.25 | 4 | 3.1 | 17 | 19 | 26 | 26 | 42 | 37 | 55 | 53.6 | 68 | 64
0.3 | 4 | 3.4 | 17 | 20 | 26 | 26 | 42 | 38 | 55 | 54 | 68 | 66
0.35 | 4 | 3.5 | 17 | 20.5 | 26 | 26 | 42 | 39 | 55 | 54.5 | 68 | 67
0.4 | 4 | 4 | 17 | 21 | 26 | 26 | 42 | 39.5 | 55 | 55 | 68 | 68
0.45 | 4 | 4 | 17 | 21.2 | 26 | 26 | 42 | 40 | 55 | 55 | 68 | 68
0.5 | 4 | 4 | 17 | 21.3 | 26 | 26.2 | 42 | 40.5 | 55 | 55 | 68 | 69
0.55 | 4 | 4 | 17 | 21.3 | 26 | 26.4 | 42 | 41 | 55 | 55 | 68 | 70
0.6 | 4 | 4.5 | 17 | 21.3 | 26 | 26.6 | 42 | 41.5 | 55 | 55 | 68 | 72
0.65 | 4 | 5 | 17 | 21.3 | 26 | 26.8 | 42 | 42 | 55 | 55.5 | 68 | 74
0.7 | 4 | 5.5 | 17 | 22 | 26 | 27 | 42 | 42 | 55 | 56 | 68 | 77
0.75 | 4 | 6 | 17 | 23 | 26 | 27.5 | 42 | 42 | 55 | 56.5 | 68 | 79
0.8 | 4 | 6.5 | 17 | 24 | 26 | 28 | 42 | 42.5 | 55 | 57 | 68 | 80
0.85 | 4 | 7 | 17 | 25 | 26 | 28.5 | 42 | 43 | 55 | 57.5 | 68 | 82
0.9 | 4 | 8 | 17 | 26 | 26 | 30 | 42 | 44 | 55 | 58 | 68 | 84
0.95 | 4 | 9 | 17 | 28 | 26 | 31 | 42 | 45 | 55 | 59 | 68 | 86
1 | 4 | 12 | 17 | 30 | 26 | 33 | 42 | 48 | 55 | 60 | 68 | 88

## Tornado
Source | Low | High | Delta
A | -0.2 | 0.8 | 1 | -2 | 8
B | -0.15 | 0.75 | 0.9 | -1.5 | 7.5
C | -0.4 | 0.5 | 0.9 | -4 | 5
D | -0.05 | 0.75 | 0.8 | -0.5 | 7.5
E | 0 | 0.6 | 0.6 | 0 | 6
F | -0.2 | 0.3 | 0.5 | -2 | 3
G | -0.3 | 0 | 0.3 | -3 | 0